## Sheet1
No. | Description of Work | Risk Category | Impact | Probabilty | Mitigating actions | Responsible
|  | RR= Resource Risk, TR = Time Risk, FR = Financial Risk, QR = Quality Risk , AR= Access Risk | How big is the impact of the risk? Scale of 1 to 5 | How likely is the risk to occur? | What will be done to reduce the risk?
1 | Security risks | AR | 5 | 1 | Implementing security controls, regularly updating software, performing regular security assessments and audits | Back-End Developer
2 | Data Intergrity Risks | AR | 4 | 1 | Restrict access to sensitive data to authorized personnel only. | Stakeholder
3 | Technical Risks | QR | 3 | 3 | Thoroughly test systems and applications before deployment to identify and fix problems. | Back-End Developer
4 | Scalabilty Risks | QR | 2 | 4 | Regularly perform load testing to identify bottlenecks and capacity constraints, and to ensure that the system can handle increasing demand. | Back-End Developer
5 | Performance Risks | QR | 3 | 2 | Implement performance monitoring tools to continuously monitor the system and detect performance issues in real-time. | Quality Assurance
6 | User Adoption Risks | RR | 2 | 2 | Engage with potential users to understand their needs and expectations, and to design the system to meet those needs. | Quality Assurance
7 | Integration Risks | QR | 2 | 2 | Use standardized interfaces and protocols, such as REST APIs, to facilitate the integration of different systems. | Back-End Developer
8 | Schedule Risks | TR | 4 | 4 | Define a realistic project scope, focusing on delivering a minimum viable product, and avoiding scope creep. | Stakeholder
9 | Maintenance Risk | RR | 1 | 4 | Implement automated testing to validate system functionality and to detect any issues early in the maintenance process. | Stakeholder